## Gantt Chart
GANTT CHART
PROJECT TITLE |  | [Project's title] |  |  |  |  | DATE | [6 empty] | 2019-08-26
PROJECT MEMBERS |  | Richard D, Ka H, Louis L, Stone S, Steven X
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Interface design and Proposal
1.1 | Logo design | All | 2019-08-26 | 2019-08-28 | 2 | 100% | bar: WEEK 1 M to WEEK 1 W; WEEK 5 M
1.2 | Interface design | All | 2019-08-27 | 2019-09-02 | 5 | 100% | bar: WEEK 1 T to WEEK 2 M; WEEK 5 M
1.3 | Proposal Writing | All | 2019-09-02 | 2019-09-09 | 7 | 100% | bar: WEEK 2 M to WEEK 3 M; WEEK 5 M
2 | Backend development
2.1 | Basic function programming | Stone S, Steven X | 2019-09-09 | 2019-09-23 | 14 | 15% | bar: WEEK 3 M to WEEK 4 M; WEEK 5 M
2.2 | Map API buiding | Ka H, Louis L | 2019-09-09 | 2019-09-27 | 18 | 0% | bar: WEEK 3 M to WEEK 5 M
2.3 | Database building | Richard D | 2019-09-09 | 2019-09-27 | 18 | 0% | bar: WEEK 3 M to WEEK 5 M
3 | Testing 1
3.1 | Basic funtion testing | Stone S, Steven X | 2019-09-23 | 2019-09-29 | 6 | 0% | bar: WEEK 4 M to WEEK 5 M
3.2 | Map API testing | Ka H, Louis L | 2019-09-23 | 2019-09-29 | 6 | 0% | bar: WEEK 4 M to WEEK 5 M
3.3 | Database testing | Richard D | 2019-09-23 | 2019-09-29 | 6 | 0% | bar: WEEK 4 M to WEEK 5 M
4 | Frontend development
4.1 | Application Layout building | Stone S, Steven X | 2019-09-29 | 2019-10-06 | 7 | 0% | bar: WEEK 5 M to WEEK 6 M
4.2 | Implementing icons and logos | Richard D, Ka H, Louis L | 2019-09-29 | 2019-10-06 | 7 | 0% | bar: WEEK 5 M to WEEK 6 M
5 | Testing 2
5.1 | Functional testing | Stone S, Steven X | 2019-10-06 | 2019-10-08 | 2 | 0% | bar: WEEK 5 M; WEEK 6 M to WEEK 6 T
5.2 | Unit testing | Richard D, Ka H, Louis L | 2019-10-06 | 2019-10-08 | 2 | 0% | bar: WEEK 5 M; WEEK 6 M to WEEK 6 T
5.3 | Integration testing | All | 2019-10-07 | 2019-10-10 | 3 | 0% | bar: WEEK 5 M; WEEK 6 T to WEEK 6 R
5.4 | Usability testing | Ka H, Louis L | 2019-10-10 | 2019-10-12 | 2 | 0% | bar: WEEK 5 M; WEEK 6 R to WEEK 6 F
5.5 | Performance testing | All | 2019-10-10 | 2019-10-13 | 3 | 0% | bar: WEEK 5 M; WEEK 6 R to WEEK 7 M
5.6 | Device testing | All | 2019-10-12 | 2019-10-14 | 2 | 0% | bar: WEEK 5 M; WEEK 6 F to WEEK 7 M
6 | Final Presentation
6.1 | Introduction Video | All | 2019-10-14 | 2019-10-21 | 7 | 0% | bar: WEEK 5 M; WEEK 7 M to WEEK 8 F
6.2 | Prepare final report | All | 2019-10-18 | 2019-10-25 | 7 | 0% | bar: WEEK 5 M; WEEK 7 F to WEEK 8 F
6.3 | Prepare manual | All | 2019-10-21 | 2019-10-25 | 4 | 0% | bar: WEEK 5 M
6.4 | Prepare presentation slides | All | 2019-10-21 | 2019-10-25 | 4 | 0% | bar: WEEK 5 M